## Compressed Log
Date | Area | Change / Decision | Impact | Status
FOUNDATION — Early 2026
Early 2026 | Architecture | Set up Next.js 14 + Firebase Auth + Zustand + Vercel deployment | Full app scaffold live | ✅ Done
Early 2026 | Onboarding | 4-step wizard: Goal → Diet → Body → Account. Calculates BMR/TDEE/macros on completion | Users get personalised calorie targets | ✅ Done
Early 2026 | Eat Tab | GPS nearby restaurants matched to sgFoodDb. Full menus with Protein/$ scores and diet fit badges | Core product differentiator live | ✅ Done
Early 2026 | Food Log | Manual entry + search. Activity log with MET calories. Water tracking | Users can log all nutrition | ✅ Done
Early 2026 | Dashboard | Calorie ring, macro bars, water ring, streak badge, daily challenges | Home screen functional | ✅ Done
Early 2026 | Move Tab | Nearby gyms/parks via Google Places above activity log | Gym discovery live | ✅ Done
Early 2026 | API Layer | All API routes built with Firebase Admin auth. Typed apiClient.ts wrapper | Secure, typed server communication | ✅ Done
Early 2026 | Streak System | SGT timezone-aware streak tracking with longestStreak | Gamification live | ✅ Done
Early 2026 | Recommendations | 8-rule rules-based recommendations engine, SGT-aware | Personalised tips on dashboard | ✅ Done
Early 2026 | Scan Feature | Camera → Claude Haiku vision → USDA → log food | Exists but accuracy too low for SG food | ⏸ Deferred
FOOD DATABASE EXPANSION — Apr–May 2026
2026-04-18 | Food DB | Initial sgFoodDb.ts: McDonald's, KFC, BK, Subway, Old Chang Kee, Ya Kun, BreadTalk, Gong Cha, 7-Eleven | First 9 outlets with verified SG macros | ✅ Done
2026-05-21 | Food DB | Added hawker dishes to SG_MACRO_FOODS: teh tarik, wonton mee, others. Source: HPB | Hawker macro estimates available | ✅ Done
2026-05-22 | Food DB | Added 30+ more chains: A&W, Jollibee, Popeyes, Nandos, Dominos, Wingstop, Starbucks, Carl's Jr., LiHo, KOI, Chagee, Mixue, Cheers, FairPrice Xpress, SaladStop, Bonchon, Wendy's + more | 40+ outlets, 520+ items total | ✅ Done
BUG FIXES & UX — 2026-05-29
2026-05-29 | Bug Fix | Food search returned 'No results' — was querying empty Firestore. Rewired to search sgFoodDb directly | Food search now works | ✅ Not pushed
2026-05-29 | Bug Fix | Protein/$ sort ranked Vanilla Soft Serve #1. Added 10g minimum protein floor before scoring | Ranking shows real high-protein value meals | ✅ Not pushed
2026-05-29 | UX Fix | Post-registration redirect changed from /dashboard → /eat | New users see GPS food discovery first | ✅ Not pushed
2026-05-29 | Data Fix | McDonald's Vanilla Soft Serve Cone price corrected: $0.50 → $1.00 | Protein/$ score now accurate | ✅ Not pushed
2026-05-29 | Tooling | Generated Stride_Price_Audit.xlsx: 522 items for manual GrabFood price verification | Price audit ready to run | ✅ Done
PENDING — Not Yet Done
TBD | Deploy | Push 4 fixes to git and deploy to Vercel (must run from local terminal) | Fixes go live on https://stride-app-rosy.vercel.app | ⏳ Pending
TBD | Navigation | Move Eat/Food tab to first position in bottom nav (currently Home/Dashboard is first) | Food discovery is the core feature — should be default view | ⏳ Pending
TBD | UX | Hide 'Open Now' filter — not backed by real business hours data | Stops showing incorrect availability | ⏳ Pending
TBD | UX | Add 'Coming Soon' state to Scan tab button | Clear user expectation, avoids confusion | ⏳ Pending
TBD | Wiring | Wire dashboard to call store.loadTodayFromServer() on mount | Dashboard shows live data on refresh | ⏳ Pending
TBD | Data | Complete price audit using Stride_Price_Audit.xlsx against GrabFood | All 520+ item prices verified and corrected | ⏳ Pending
TBD | UX | Dashboard empty state for first-time users | Better first-run experience | ⏳ Pending
TBD | UX | Add skeleton loaders across all pages | No blank screens on slow connections | ⏳ Pending
TBD | Feature | Wire Profile edit page to PUT /api/profile | Users can save profile changes | ⏳ Pending
STRATEGIC DECISIONS — 2026-05-29
2026-05-29 | Principle | Reliability is #1 priority above new features. Wrong data destroys trust faster than missing features. | Every feature decision filtered through data reliability first | ✅ Decided
2026-05-29 | Data Process | All sgFoodDb updates require source, verified flag, and lastVerified date. Quarterly price sweeps via GrabFood. | Traceable, auditable food database | ✅ Decided
2026-05-29 | Scan Feature | Scan deferred — not cancelled. Revisit when SG food recognition improves or barcode scan is built as simpler step. | Users not misled by inaccurate AI food ID | ⏸ Deferred — revisit
2026-05-29 | Exercise | Structured workout routines planned for Phase 2. Activity logging (MET-based) already live. | /workouts stub exists, builds after nutrition MVP is stable | 🔵 Phase 2
2026-05-29 | GrabFood/Foodpanda | Two paths: (A) scrape data for price/menu sync, (B) official partnership for data feed. Evaluate post-MVP. | Open question — manual GrabFood use for now, partnership long-term | ⏳ Open
2026-05-29 | Notifications | Push notifications (daily reminders, streak alerts, weekly recap) planned Phase 2 via Firebase FCM. | Build after core reliability confirmed — premature notifs drive uninstalls | 🔵 Phase 2
2026-05-29 | Rewards | Deeper gamification (badges, XP, leaderboards) is Phase 2. Streak + daily challenges already live. | Accuracy-first — reliable data retains users more than rewards | 🔵 Phase 2

## Decision Log
Date | Decision Area | Decision Made | Why / Reasoning | Alternatives Considered | Status
FOOD RANKING & SCORING DECISIONS
Early 2026 | Ranking Metric | Use Protein/$ (g per SGD) as primary food value score | Singapore users are budget-conscious. Protein is the hardest macro to optimise cheaply. Protein/$ lets users find the best value high-protein meals near them — this is the core product differentiator. | Calorie/$ (too broad), Protein/calorie (ignores price), Raw protein (ignores value) | ✅ Live
Early 2026 | Protein/$ Formula | proteinPerDollar(protein, price) = round((protein / price) × 10) / 10 | Simple, transparent, one decimal place. Users can verify it mentally. e.g. 30g protein at $5 = 6.0 g/$ | Weighted composite score (too opaque), Protein density (ignores price) | ✅ Live
Early 2026 | RestaurantTier Schema | 3 tiers: full_menu (verified chain data), estimated_menu (hawker, uses macroDbRef), place_only (GPS only, no menu) | Chains have official nutrition PDFs — can show exact macros. Hawker stalls vary by cook — use HPB estimates referenced from SG_MACRO_FOODS. place_only avoids showing bad data for unverified outlets. | Single tier with confidence flags (harder for frontend), No tiers (forced all outlets to show data) | ✅ Live
Early 2026 | ServiceType Array | serviceTypes: ['dine_in', 'grab_go', 'delivery'] — always an array, never a single string | Outlets can serve multiple modes (e.g. McDonald's is dine_in + grab_go + delivery). Array future-proofs filter logic in Eat tab. | Single string field (breaks multi-mode outlets), Boolean flags per type (verbose schema) | ✅ Live
Early 2026 | macroDbRef Field | estimated_menu items reference SG_MACRO_FOODS via macroDbRef string ID instead of duplicating macro values | Hawker dishes are the same macro profile regardless of which kopitiam you order from. Single source of truth in SG_MACRO_FOODS — update one entry, all hawker outlets reflect it automatically. | Duplicate macros per outlet (gets out of sync), Always hardcode (no shared source) | ✅ Live
2026-05-29 | Protein/$ Minimum Floor | Items with < 10g protein score 0 in Protein/$ ranking — they fall to the bottom | Without a floor, cheap desserts/drinks dominated the ranking. Vanilla Soft Serve at $0.50 (4g protein) scored 8 g/$ and ranked #1 — above KFC Original Recipe (29g protein, 7.6 g/$). The metric is meaningless below a minimum protein threshold. | 5g floor (too low, still shows drinks), 20g floor (too aggressive, removes valid snacks), No floor (broken ranking) | ✅ Done, not pushed
2026-05-29 | Post-Onboarding Routing | After registration, redirect to /eat instead of /dashboard | New users have no logged data yet — the dashboard shows an empty calorie ring. The Eat tab shows immediate value: GPS food discovery near them. First impression should be the product's core differentiator, not an empty chart. | Stay on /dashboard (existing — shows empty state), Onboarding tips screen (more work, deferred) | ✅ Done, not pushed
2026-05-29 | Scan Feature Deferral | Deliberately delay the food scan feature. Show 'Coming Soon' instead of disabling silently. | Claude Haiku vision identifies US food well but misidentifies SG-specific dishes (e.g. banana → sushi). Shipping inaccurate scan results damages trust more than not having the feature. Revisit when a SG-specific food recognition model or training data is available. | Ship with low confidence warning (still shows wrong food), Restrict to packaged barcodes only (different feature), Keep as-is hidden (confusing to users who find it) | ⏸ Deferred
NAVIGATION & UX DECISIONS
2026-05-29 | Eat Tab as First Page | Move Eat/Food tab to first position in bottom nav. Make it the default landing page after login. | Food discovery is the core differentiator — it's what makes Stride different from MyFitnessPal. Dashboard is useful once a user has data, but on first open and for returning users, Eat is the most action-oriented tab. Protein/$ scoring is the hook. | Keep Dashboard first (generic, empty for new users), Home as lobby with tab shortcuts (adds navigation layer) | ⏳ Pending
FOOD DATABASE DECISIONS
Early 2026 | Local TypeScript File vs Firestore | Store Singapore restaurant/menu data in sgFoodDb.ts (local TypeScript file), not Firestore | Menu data is curated, versioned, and changes rarely. Keeping it in the TypeScript file means: zero latency (no DB call), works offline, no Firestore read costs, type-safe. Community user-submitted foods go to Firestore separately. | All data in Firestore (latency + cost), JSON file (no type safety), Both duplicated (sync problem) | ✅ Live
Early 2026 | Source Verification Flags | Every menu item has source ('official_sg' ¦ 'hpb' ¦ 'community' ¦ 'usda') and verified (bool) fields | Macro accuracy varies wildly by source. Users and the team need to know confidence level. official_sg = brand's own SG PDF (highest trust). hpb = Singapore government nutrition data. community = estimated, treat as approximate. | Single verified boolean (loses source info), No flags (no way to prioritise corrections) | ✅ Live
2026-05-29 | Price Verification Process | Quarterly price sweeps using GrabFood as primary source. Corrections applied via audit spreadsheet → Claude → sgFoodDb in one pass. | Prices change more often than macros. McDonald's cone was $0.50 in DB but $1.00 in real life — wrong Protein/$ score. GrabFood always shows live SG prices. Batch correction via spreadsheet is faster than editing sgFoodDb line by line. | Manual ad-hoc fixes (too slow, misses items), Automated price scraping (legal risk, maintenance overhead) | ⏳ Process agreed, first audit pending
RELIABILITY & DATA QUALITY — ONGOING PRINCIPLE
2026-05-29 | Core Priority | Reliability is the #1 priority above all features | An app that shows wrong calorie data is worse than an app with fewer features. Users making food and fitness decisions based on bad data lose trust immediately and never return. Every feature decision must ask: does this make the data more or less reliable? | Features-first approach (deferred reliability), Best-effort data (acceptable for v1) | ✅ Decided
2026-05-29 | Data Push Reliability | All writes use optimistic UI + background sync. Never block the UI on a Firestore write. Always verify the right data fields are being pushed. | Users should never wait for a server response to see their log update. But silent failures are a risk — if the background push fails, data is lost. Schema discipline (correct field names, types, subcollection paths) prevents silent data corruption. | Await all writes (UI feels slow), Fire-and-forget with no validation (data corruption risk) | ✅ Decided
2026-05-29 | Database Update Process | sgFoodDb.ts is the single source of truth for SG restaurant data. Updates go through: research → verify source → add with correct source/verified/lastVerified fields → push to git. | Ad-hoc edits without source verification introduce untracked errors (e.g. McDonald's cone at $0.50). Every entry must have a traceable source. The price audit process (quarterly GrabFood sweep) is the ongoing maintenance mechanism. | Crowdsourced edits (low quality control), Manual one-off fixes (no audit trail) | ✅ Decided
SCAN FEATURE — FUTURE ROADMAP
2026-05-29 | Scan Feature — Revisit Criteria | Scan is deferred, not cancelled. Revisit when: (1) a SG-specific food recognition dataset exists, or (2) barcode scan for packaged food is built as a simpler first step. | Current failure mode: Claude Haiku identifies US-centric food. Banana → sushi misidentification. SG dishes (chicken rice, char kway teow, laksa) have no reliable training data in general vision models. Barcode scan for packaged goods (NTUC, Cheers products) is a more solvable problem short-term. | Ship with low-confidence warning (still wrong), Use USDA only (no SG dishes), Wait for GPT-4V improvement | ⏸ Deferred — revisit
EXERCISE & WORKOUT FEATURES — FUTURE
2026-05-29 | Exercise Routine Feature | Add structured exercise routine / workout plan feature to the app. Decision: build in Phase 2 after core nutrition MVP is stable. | Activity logging (manual, MET-based) already exists. Structured workouts (sets/reps, rest timers, progressive overload) is a separate feature set. The /workouts stub page exists. Building this before nutrition is solid would split focus — users come for food tracking first. | Build now alongside food (splits focus), Third-party integration only (no own data), Stub forever | 🔵 Future — Phase 2
GRABFOOD / FOODPANDA INTEGRATION — FUTURE
2026-05-29 | GrabFood/Foodpanda Data Strategy | Two potential approaches: (A) Extract/scrape menu + price data from GrabFood/Foodpanda to keep sgFoodDb current automatically. (B) Partnership — deep-link to their app with macro pre-fill, or receive official data feed. Decision: open, needs evaluation. | GrabFood has live SG prices and menus for most chains. Scraping is legally grey and technically fragile (changes break it). An official data partnership gives clean, maintained data but requires business development. Short-term: use GrabFood manually for price verification. Long-term: pursue partnership if Stride gains traction. | Build scraper now (legal risk, maintenance overhead), Ignore and update manually (doesn't scale), Build partnership now (too early, no leverage) | ⏳ Open — evaluate post-MVP
RETENTION — NOTIFICATIONS & REWARDS — FUTURE
2026-05-29 | Push Notifications | Add push notifications for: daily meal logging reminders, streak at-risk warnings, weekly recap. Decision: Phase 2 — build after core reliability is confirmed. | Retention depends on habit formation. Push notifications are the standard mechanism. However, notifications sent before the core app is reliable and accurate will drive uninstalls. Users need to trust the data before reminders to use it are valuable. Infrastructure: Firebase Cloud Messaging (FCM) already supported by Firebase stack. | Build now (distraction from reliability), Never (loses retention lever), Third-party (Braze, OneSignal) — adds cost | 🔵 Future — Phase 2
2026-05-29 | Rewards & Gamification | Expand gamification beyond streaks: milestone badges, weekly challenges, leaderboards, XP system. Decision: streak + daily challenges are live (Phase 1). Deeper rewards are Phase 2. | Streak badge and daily challenges already ship with the app. Research shows gamification drives retention in fitness apps (Fitbit, Nike Run Club). But complexity of rewards systems can be a distraction. The most impactful retention lever right now is data accuracy — if users trust their macro data, they return naturally. | Full XP system now (over-engineered for MVP), No gamification (streak already there), Leaderboards only (social not yet built) | 🔵 Future — Phase 2

## Detailed Log
Date | Session | Type | What Was Done | File(s) Changed | Status | By | Notes
FOUNDATION BUILD — Early 2026
Early 2026 | 1 | Feature | Firebase Auth (email/password), Zustand store, Tailwind CSS, Vercel deployment | src/lib/firebase.ts, store.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | 4-step onboarding wizard. Calculates BMR/TDEE/macros using Mifflin-St Jeor | src/app/register/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Dashboard: calorie ring, macro bars, water ring, streak, challenges | src/app/(dashboard)/dashboard/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Eat tab: GPS → sgFoodDb match → menus with Protein/$ and diet badges | src/app/(dashboard)/eat/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Food log, activity log, water tracking | src/app/(dashboard)/log/ | ✅ Done | Dev
Early 2026 | 1 | Feature | Move tab: nearby gyms + parks via Google Places | src/app/(dashboard)/move/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Me tab: profile, streak, weight log, sign out, reset app | src/app/(dashboard)/me/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | All API routes with Firebase Admin auth | src/app/api/*/route.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Streak system: SGT timezone-aware, longestStreak tracking | src/app/api/streak/route.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Recommendations engine: 8 rules, SGT-aware | src/app/api/recommendations/route.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Google Places cache: 10-min TTL, 1km grid | src/app/api/nearby-places/route.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Typed API client wrapper | src/lib/apiClient.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | AuthGuard: redirects unauthenticated users to /login | src/components/AuthGuard.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Scan: camera → Claude Haiku → USDA → log | src/app/(dashboard)/scan/page.tsx | ⏸ Deferred | Dev | SG food accuracy too low
FOOD DATABASE EXPANSION — Apr–May 2026
2026-04-18 | 2 | Data | Initial 9 outlets added to sgFoodDb.ts with official SG macros | src/lib/sgFoodDb.ts | ✅ Done | Dev
2026-05-21 | 3 | Data | Hawker dishes added to SG_MACRO_FOODS (teh tarik, wonton mee, etc). Source: HPB | src/lib/sgFoodDb.ts | ✅ Done | Dev
2026-05-22 | 4 | Data | 30+ chains added. Total: 40+ outlets, 520+ items | src/lib/sgFoodDb.ts | ✅ Done | Dev | Wendy's, A&W, Jollibee, Popeyes, Starbucks, Mixue, LiHo, KOI, Cheers, FairPrice Xpress + more
BUG FIXES — 2026-05-29
2026-05-29 | 5 | Bug Fix | Food search returned No results — rewired to search sgFoodDb directly | src/app/(dashboard)/log/food/page.tsx | ✅ Not pushed | Claude | Was querying empty Firestore. Now searches searchAll() + SG_MACRO_FOODS + Firestore fallback
2026-05-29 | 5 | Bug Fix | Protein/$ sort ranked Vanilla Soft Serve #1. Added 10g protein floor | src/app/(dashboard)/eat/page.tsx | ✅ Not pushed | Claude | Applied in both individual item sort and restaurant-level sort
2026-05-29 | 5 | UX | Post-onboarding redirect /dashboard → /eat | src/app/register/page.tsx | ✅ Not pushed | Claude
2026-05-29 | 5 | Data | McDonald's cone price $0.50 → $1.00 | src/lib/sgFoodDb.ts | ✅ Not pushed | Claude | lastVerified updated to 2026-05-29
2026-05-29 | 5 | Tooling | Generated Stride_Price_Audit.xlsx (522 items) | outputs/Stride_Price_Audit.xlsx | ✅ Done | Claude
2026-05-29 | 5 | Docs | Created CHANGELOG.md, PARTNER_BRIEFING.md, Stride_Work_Log.xlsx | Repo root + outputs | ✅ Done | Claude
PENDING
TBD | — | Deploy | git push origin main from local terminal | All | ⏳ Pending | Dean
TBD | — | Nav | Move Eat tab to first position in bottom nav | src/components/layout/BottomNav.tsx | ⏳ Pending | Claude | Discussed — Eat is core feature, should be first
TBD | — | UX | Hide 'Open Now' filter (no real business hours data) | eat/page.tsx | ⏳ Pending | Claude
TBD | — | UX | Add Coming Soon state to Scan tab | scan/page.tsx | ⏳ Pending | Claude
TBD | — | Wiring | Wire dashboard to loadTodayFromServer on mount | dashboard/page.tsx | ⏳ Pending | Claude
TBD | — | Data | Complete price audit (GrabFood sweep) | sgFoodDb.ts | ⏳ Pending | Dean + Claude | Use Stride_Price_Audit.xlsx

## Summary
STRIDE — PROJECT SUMMARY
WHAT IT IS
Stride is a dark-themed, gamified fitness and nutrition tracking app for Singapore users.
Core differentiator: GPS-based nearby restaurant discovery with Protein/$ value scoring.
Live at: https://stride-app-rosy.vercel.app ¦ Stack: Next.js 14 · Firebase · Zustand · Vercel
BUILD STATUS AS OF 2026-05-29
✅ App is ~MVP-ready. All core features work on mobile.
✅ 40+ Singapore restaurant outlets, 520+ menu items in food database.
✅ GPS food discovery, food logging, activity, water, weight, streak all functional.
⚠️ 4 code fixes written but NOT YET pushed to Vercel — need git push from local terminal.
⏸ Scan feature intentionally deferred (SG food ID accuracy too low).
IMMEDIATE NEXT STEPS (in order)
1. PUSH TO GIT: cd 'C:\Users\user\OneDrive\Fitness App' && git add -A && git commit && git push origin main
2. Move Eat tab to first position in bottom nav (it's the core feature)
3. Hide 'Open Now' filter in Eat tab (no real business hours data)
4. Add 'Coming Soon' state to Scan tab
5. Wire dashboard to load today's data on mount
6. Complete price audit (Stride_Price_Audit.xlsx + GrabFood sweep)
HOW TO USE THIS LOG IN FUTURE CHATS
Paste the contents of PARTNER_BRIEFING.md at the start of any new chat.
Ask Claude to update Stride_Work_Log.xlsx after completing any work.
Add new rows to Compressed Log and Detailed Log. Add decisions to Decision Log.
KEY FILES
CLAUDE.md — Full developer guide. Read first.
CHANGELOG.md — Running fix log, most recent first.
PARTNER_BRIEFING.md — Paste into any new chat for full context.
Stride_Work_Log.xlsx — This file. Update after every session.
Stride_Price_Audit.xlsx — 522-item price verification spreadsheet.
src/lib/sgFoodDb.ts — Singapore food database (~13,000 lines).