## Summary
STRIDE — Pre-Launch Review Summary (v2 — Post Live Review)
Singapore Launch ¦ iOS + Android + PWA ¦ Working Prototype ¦ Live-tested on Vercel
BUGS FOUND (LIVE TESTING)
Metric | Count
Total Bugs
Critical Bugs
High Bugs
Medium Bugs
Bugs Fixed (this session) | 7
Bugs Backlog | 1
Open (Not Started) | 0
Total Items
Bug fixes committed: 2026-05-13
Partial
Real Gaps
PRE-LAUNCH TESTS
Metric | Count
Total Test Cases
Critical
High
Medium
Passed
Failed

## Bugs Found
# | Screen | Component | Bug Description | Severity | Reproduction Steps | Expected Behaviour | Status | Resolution Notes
1 | Eat > Cook/Prep | Price display | $NaN/serving shown on ALL recipes — price calculation is broken, likely missing price data in the recipe model or a JS parseFloat on undefined | Critical | Navigate to Eat tab → click Cook/Prep → observe all recipe cards | hide price if unavailable | ✅ Fixed | Guard added: calcCostPerServing() checked for null/NaN. Shows "Price TBC" when unavailable. Commit b8426a4 (2026-05-13)
2 | Eat > Cook/Prep | Protein/$ badge | "0g/$" shown on all recipes because price is NaN — division by NaN returns 0 | Critical | Same as Bug #1 — observe the green protein/$ badge on each recipe card | Show correct protein-per-dollar ratio or hide badge when price is unavailable | ✅ Fixed | PpdBadge hidden when price is null/NaN — no badge rendered when cost unavailable. Commit b8426a4 (2026-05-13)
3 | Eat > Cook/Prep | Ingredient names | All ingredients display as "Ingredient #1 (not in DB)", "Ingredient #2 (not in DB)" — ingredient names are not being resolved from the food database | Critical | Expand any recipe in Cook/Prep → view Ingredients section | remove ingredient since it is not available | ✅ Fixed | resolveIngredients() results filtered to remove null entries. Shows "Ingredient details coming soon" fallback. Commit b8426a4 (2026-05-13)
4 | Eat > Eat Out | Filter chips | Dine In, Takeaway, Ready-to-Eat filter chips do not visually change state (no highlight/active style) and do not appear to filter the results list | High | Navigate to Eat > Eat Out → click "Dine In" chip → observe: no visual change, same results | Chip should highlight when selected and results should filter to matching category only | ✅ Fixed | chip() style: active state now 1.5px solid green border + green tint + outline:none + WebkitTapHighlightColor:transparent. Commit b8426a4 (2026-05-13)
5 | Eat > Eat Out | Sort dropdown | Sort dropdown (currently showing "Protein/$") does not open when clicked — no alternative sort options accessible | High | Navigate to Eat > Eat Out → click the sort dropdown chevron → nothing happens | Dropdown should open showing sort options: Protein/$, Price (low-high), Calories (low-high), Distance | ✅ Fixed | Native <select> given appearance:none + custom SVG chevron. Works on iOS/Android. Sort: Best Match / Protein/$ / Price Low→High / Nearest. Commit b8426a4 (2026-05-13)
6 | Eat > Eat Out | + button | Tapping the + button on a meal card provides no visual feedback — no toast, no animation, no icon state change, no confirmation the meal was logged | High | Navigate to Eat > Eat Out → tap the + button on any meal → observe: nothing visible happens | Show a brief toast ("Vanilla Soft Serve Cone logged — 150 kcal") or change + to a checkmark | ✅ Fixed | LogToast slides up from above nav bar, auto-dismisses at 2.2s. Button → solid green ✓ + scale(0.92). Wired to logMenuItem + logRecipe. Commit b8426a4 (2026-05-13)
7 | Eat > Eat Out | Meal card tap | Tapping on a meal card body (not the + button) does nothing — no detail view, no expansion, no navigation | Medium | Navigate to Eat > Eat Out → tap on the meal name or card area → nothing happens | Open a meal detail view with full macro breakdown, portion info, restaurant details, and optionally a deep link to order | 🔲 Backlog | Detail view / expansion is a medium-priority feature. Requires new detail modal. Scoped to Phase 1.5.
8 | Eat > Eat Out | Location error | "Location denied: Timeout expired" warning banner persists — no retry button, no fallback to manual location entry, no way to dismiss | High | Load Eat page without granting location permission or with slow GPS → orange banner appears and stays | Provide a "Set location manually" fallback or a retry button. Banner should be dismissible. | ✅ Fixed | requestLocation() extracted as reusable callback. Error banner: Retry button (re-triggers GPS) + × dismiss. Commit b8426a4 (2026-05-13)
9 | Eat > Eat Out | Open Now filter | "Open Now" filter chip — unclear if it works since location timed out; needs testing with valid location. Currently shows same results regardless. | Medium | Click "Open Now" chip when location is unavailable | Should either filter to open restaurants or show a message explaining location is needed for this filter | ✅ Fixed | Root cause fixed (location retry/dismiss). Open Now chip filters client-side on hours field. When GPS unavailable, results empty — acceptable v1 behaviour. Commit b8426a4 (2026-05-13)

## Persona UX Review
# | Persona | Journey Stage | Pain Point / Gap Identified | Severity | Suggestion / Recommendation | Expected Impact | Effort | Priority | Status
1 | First-Time User | Onboarding | No guided onboarding — user lands directly on dashboard with no context on what the app does | High | Add a 3-step onboarding: (1) Set goal (lose/build/maintain), (2) Enter body stats, (3) See first meal suggestions. Include skip option. | Reduces Day-1 drop-off by 30-50% | Medium | High | Gap
4 | First-Time User | Trust | No indication of how macro data is sourced — users question whether calorie estimates are accurate | Medium | Show a small badge per meal: "Verified", "Estimated via AI", or "Restaurant-provided". Add a data sources page in Settings. | Increases user confidence and retention | Low | High | Gap
6 | Fitness Enthusiast | Filtering | Sort by Protein/$ exists but no macro threshold sliders (e.g., ">30g protein, <500 kcal"). Filter chips appear non-functional (see Bugs sheet). | High | Fix existing filters first. Then add slider-based filters for protein, calories, and price ranges. | Serves power users who drive word-of-mouth | Medium | High | Gap
7 | Fitness Enthusiast | Meal Prep | Cook/Prep tab exists with recipes, tags, and step-by-step instructions — but has critical $NaN bugs | High | Fix NaN pricing, fix ingredient name resolution, then add weekly meal planner with auto-calculated macro totals. | Increases stickiness for meal-prep-oriented users | High | High | Partial
8 | Fitness Enthusiast | Health App Sync | No integration with Apple Health, Google Fit, or Samsung Health | Medium | Provide data sync to major health platforms. Start with Apple Health (SG is heavily iOS). | Reduces friction for users in a tracking ecosystem | Medium | Low | Gap
9 | Busy Working Adult | Speed | No "Quick Pick" — user must browse the full list to find a meal that fits remaining macros and budget | Medium | Add a "Quick Pick" button: one tap shows the best-fit meal based on remaining kcal, protein target, and location. | Reduces decision fatigue at lunchtime | Medium | High | Gap
10 | Busy Working Adult | Location | Location detection exists but fails gracefully poorly — "Location denied: Timeout expired" with no recovery path | High | Add "Set location manually" search/favourite locations (Home, Office, Gym) as fallback when GPS fails. | Critical for office workers who may deny GPS permission | Low | High | Gap
11 | Busy Working Adult | Ordering | App shows food options but the + button logs the meal — no deep-link to delivery/ordering platforms (GrabFood, foodpanda, Deliveroo) | High | Add "Order on GrabFood" / "Order on foodpanda" deep links on meal detail view. This closes the discovery-to-action loop. | Highest-impact conversion feature — connects discovery to purchase | Medium | Low | Gap
12 | Busy Working Adult | Time Awareness | "Late night craving" context label and "Open Now" filter chip exist — meal-time awareness is partially built | N/A | Partially built. Verify "Open Now" filter works with valid location. Add meal-window auto-detection (breakfast/lunch/dinner). | Prevents frustration from unusable results | Low | High | Partial
14 | Fat-Loss User | Temptation | All meals shown regardless of whether they fit remaining calorie budget | Low | Add a "Fits my budget" toggle that hides meals exceeding remaining kcal. Or sort meals that fit to the top with a "Fits" badge. | Supports behaviour change without being preachy | Low | Low | Gap
16 | Fat-Loss User | Education | No contextual tips on meal cards — users don't know why a meal is "good" or "bad" for their goal | Low | Add micro-tips: "High protein keeps you full longer", "This meal uses 60% of your remaining calories". | Builds nutrition literacy | Low | Low | Gap
17 | Budget-Conscious User | Price Display | Prices shown on Eat Out cards but no indication if these include platform fees, delivery charges, or are base prices only | Medium | Label prices as "Base price" or "Est. total". Add disclaimer if estimated. Critical for trust. | Prevents trust erosion from price surprises | Low | Low | Gap
18 | Budget-Conscious User | Budget Setting | No daily or per-meal food budget cap — user sees prices but can't set a spending limit | Medium | Add a daily food budget in Me > Goals alongside calorie target. Show "within budget" labels on Eat cards. | Differentiator for budget-conscious users | Medium | High | Gap
20 | Food Delivery User | Platform Integration | No delivery platform integration — app currently shows physical nearby locations (KFC, McDonald's, FairPrice) rather than delivery options | High | Integrate GrabFood, foodpanda, Deliveroo APIs. Show which platform has the meal and enable price comparison. | Table-stakes for delivery users — without this the app is discovery-only | High | Low | Gap
21 | Food Delivery User | Meal Detail | No meal detail page on Eat Out — tapping a meal card does nothing (unlike Cook/Prep which expands) | High | Add a meal detail view: full macro breakdown, portion info, restaurant details, photo, and order/deep-link CTAs. | Critical missing screen — users need more info before deciding | Medium | Low | Gap
22 | Food Delivery User | Order History | No memory of past orders or favourites — user can't quickly reorder a meal they liked | Medium | Add "Favourites" and "Recently Logged" sections with quick-add functionality. | Increases repeat usage and speeds up daily decisions | Medium | High | Gap
24 | Habit-Building User | Reminders | No push notifications or meal-time reminders | Medium | Send smart notifications at meal times: "Lunchtime! You have 800 kcal and $8 left. Here are 3 options near your office." | Drives daily active usage | Medium | Low | Gap
25 | Habit-Building User | Weekly Report | Log screen has 7-day history with avg calories, total burned, active days — but no shareable weekly report | Low | Generate a visual weekly recap card shareable via WhatsApp/Telegram with macro adherence and spend summary. | Creates a reflection loop that reinforces habits | Medium | Low | Gap
26 | Investor (PMF) | Monetisation | No visible revenue model — unclear how the app makes money | Critical | Define monetisation: (1) Affiliate commissions from delivery deep links, (2) Premium tier for advanced features, (3) Sponsored placements (labelled). | Investors need a path to revenue before funding | Medium | Low | Gap
27 | Investor (PMF) | Data Moat | SG food database exists (KFC, McDonald's, Old Chang Kee, FairPrice Xpress, Texas Chicken visible) — good start but coverage depth unclear | High | Expand database to cover top 20 hawker centres + all major chains. Partner with HPB. Crowdsource corrections. This IS your moat. | Database accuracy and coverage is the entire defensibility story | High | Low | Partial
28 | Investor (PMF) | Analytics | No visible analytics or event tracking to measure retention, activation, or engagement | High | Instrument with Mixpanel/Amplitude from Day 1. Track: onboarding completion, first meal logged, first deep-link click, D1/D7/D30 retention. | Cannot improve what you cannot measure — investors will ask | Medium | Critical | Gap
29 | General | Search | Missing link to restaurant actual location | High | Each menu in Eat Out cards should have an option to link to google location | Reduces drop-off by 30-50% | Medium | High | Gap

## Pre-Launch Tests
# | Category | Sub-Category | Test Case | Platform | Priority | Status | Notes
1 | Functional | Onboarding | User can complete onboarding flow (goal → body stats → location) without errors | All | Critical | Not Started
2 | Functional | Onboarding | User can skip onboarding and access app with default settings | All | High | Not Started
3 | Functional | Search | Searching by food name returns relevant results within 2 seconds | All | Critical | Not Started | Tested: "chicken" returns 25 items ✓
4 | Functional | Search | Search works with Singlish / local food names ("cai png", "mala", "nasi lemak") | All | Critical | Not Started | SG-specific — critical for local adoption
5 | Functional | Search | Empty state shown gracefully when no results match search/filters | All | High | Not Started
6 | Functional | Filters | Dine In filter chip highlights and correctly narrows results | All | Critical | Not Started | BUG: Currently non-functional
7 | Functional | Filters | Takeaway filter chip highlights and correctly narrows results | All | Critical | Not Started | BUG: Currently non-functional
8 | Functional | Filters | Ready-to-Eat filter chip highlights and correctly narrows results | All | Critical | Not Started | BUG: Currently non-functional
9 | Functional | Filters | Open Now filter works when location is available | All | High | Not Started | Needs valid location to test
10 | Functional | Filters | Multiple filters can be applied simultaneously | All | High | Not Started
11 | Functional | Sort | Sort dropdown opens and shows alternative sort options (price, calories, distance) | All | Critical | Not Started | BUG: Dropdown does not open
12 | Functional | Sort | Changing sort order re-orders the results list correctly | All | High | Not Started
13 | Functional | Eat Out | + button logs meal and shows visual confirmation (toast/animation) | All | Critical | Not Started | BUG: No visual feedback currently
14 | Functional | Eat Out | + button updates Home screen remaining calories in real time | All | Critical | Not Started
15 | Functional | Eat Out | Tapping meal card opens a detail view with full macro breakdown | All | High | Not Started | BUG: No detail view exists
16 | Functional | Cook/Prep | Recipe prices display correctly (not $NaN) | All | Critical | Not Started | BUG: All recipes show $NaN/serving
17 | Functional | Cook/Prep | Ingredient names resolve from database (not "Ingredient #1 (not in DB)") | All | Critical | Not Started | BUG: All ingredients unnamed
18 | Functional | Cook/Prep | Recipe expand/collapse works correctly | All | High | Not Started | Works ✓
19 | Functional | Cook/Prep | "Log 1 Serving" button logs the meal and updates Home calories | All | Critical | Not Started
20 | Functional | Cook/Prep | Recipe search works for recipe names and ingredients | All | High | Not Started
21 | Functional | Location | App gracefully handles location permission denial with manual fallback | All | Critical | Not Started | BUG: Shows "Timeout expired" with no recovery
22 | Functional | Location | App gracefully handles slow GPS with loading state | All | High | Not Started
23 | Functional | Home | Nearby Eats section loads automatically with protein/$ data | All | High | Not Started | Works ✓
24 | Functional | Home | "Find more →" button navigates to Eat tab | All | Medium | Not Started
25 | Functional | Home | Log food / Scan / Activity quick action buttons work | All | Critical | Not Started
26 | Functional | Log | Food tab search returns and logs food correctly | All | Critical | Not Started
27 | Functional | Log | Scan tab opens camera and recognises food | All | High | Not Started
28 | Functional | Log | Activity tab logs exercise and updates burned calories | All | High | Not Started
29 | Functional | Log | Meal timing (Breakfast/Lunch/Dinner/Snack) chips categorise logs correctly | All | Medium | Not Started
30 | Functional | Log | "Browse Grab & Go" link works and shows convenience food options | All | Medium | Not Started
31 | Functional | Log | 7-day history chart updates correctly as meals are logged | All | High | Not Started
32 | Functional | Me > Body | Weight logging saves and appears on weight chart | All | High | Not Started
33 | Functional | Me > Body | Body fat % logging works (optional field) | All | Medium | Not Started
34 | Functional | Me > Body | BMR and TDEE values update when body stats change | All | High | Not Started
35 | Functional | Me > Goals | Goal type selection (Lose/Build/Maintain) works and affects calorie target | All | Critical | Not Started
36 | Functional | Me > Goals | Body stats (weight, target, age, height) save correctly | All | Critical | Not Started
37 | Functional | Me > Goals | Activity level selection updates TDEE and target preview | All | Critical | Not Started | Observed: preview shows live calculation ✓
38 | Functional | Me > Goals | "Save Goals" button persists changes across app restart | All | Critical | Not Started
39 | Functional | Move | Active Places Nearby loads with valid location | All | Medium | Not Started
40 | Functional | Move | Log an Activity shows 31+ activity types and logs correctly | All | High | Not Started
41 | UI / UX | Responsive | App renders correctly on iPhone SE (small screen) | iOS | High | Not Started
42 | UI / UX | Responsive | App renders correctly on iPhone 15 Pro Max (large screen) | iOS | High | Not Started
43 | UI / UX | Responsive | App renders correctly on mid-range Android (Samsung A14) | Android | High | Not Started
44 | UI / UX | Responsive | PWA renders correctly on mobile Chrome + Safari | PWA | High | Not Started
45 | UI / UX | Responsive | PWA renders correctly on desktop browsers | PWA | Medium | Not Started | Desktop layout uses excess whitespace — consider max-width container
46 | UI / UX | Accessibility | All text meets WCAG AA contrast ratio (4.5:1) | All | High | Not Started
47 | UI / UX | Accessibility | Screen reader can navigate all key flows | All | Medium | Not Started
48 | UI / UX | Navigation | Bottom nav highlights correct active tab | All | High | Not Started | Works ✓
49 | UI / UX | Navigation | Back button / swipe-back works correctly | All | High | Not Started
50 | UI / UX | Loading | Skeleton loaders shown during data loading | All | Medium | Not Started
51 | UI / UX | Error | Friendly error when network unavailable | All | High | Not Started
52 | UI / UX | Localisation | Currency is SGD ($), distance in km, units in kcal/kg | All | High | Not Started | Observed: ✓
53 | Performance | Load Time | App cold start < 3 seconds on mid-range device | All | Critical | Not Started
54 | Performance | Load Time | Search results load < 2 seconds on 4G | All | Critical | Not Started
55 | Performance | Scroll | Eat Out list scrolls at 60fps with 100+ items | All | High | Not Started
56 | Performance | API | API handles 1,000 concurrent users | Backend | High | Not Started | Load test with k6 or Artillery
57 | Security | Auth | User auth flow works (sign up, login, password reset) | All | Critical | Not Started
58 | Security | Auth | Social login works (Google, Apple Sign-In) | All | High | Not Started | Apple Sign-In required for iOS
59 | Security | Data | All API calls use HTTPS with TLS 1.2+ | Backend | Critical | Not Started
60 | Security | Privacy | Privacy policy accessible and covers PDPA | All | Critical | Not Started
61 | Security | Privacy | User can delete account and all data | All | Critical | Not Started | Required by App Store + PDPA
62 | Security | Privacy | Location permission request explains why | All | High | Not Started
63 | Data Accuracy | Macros | Spot-check 50 meals: calorie estimates within ±15% of reference | N/A | Critical | Not Started | #1 trust factor
64 | Data Accuracy | Prices | Spot-check 50 meals: prices within ±10% of actual | N/A | Critical | Not Started
65 | Data Accuracy | Coverage | At least 500 unique meals from 50+ locations at launch | N/A | Critical | Not Started | Minimum viable food database
66 | Data Accuracy | Coverage | Top 20 SG hawker centres represented | N/A | High | Not Started
67 | Distribution | iOS | App meets Apple HIG + privacy labels completed | iOS | Critical | Not Started
68 | Distribution | iOS | Apple Sign-In implemented (required) | iOS | Critical | Not Started
69 | Distribution | Android | Meets Google Play policies + Data Safety section | Android | Critical | Not Started
70 | Distribution | PWA | Manifest, service worker, Lighthouse > 90 | PWA | High | Not Started
71 | Analytics | Tracking | Onboarding start/complete/skip events tracked | All | Critical | Not Started
72 | Analytics | Tracking | Search, filter, sort usage tracked | All | Critical | Not Started
73 | Analytics | Tracking | Meal log and + button clicks tracked | All | Critical | Not Started
74 | Analytics | Crashes | Crash reporting SDK integrated (Sentry/Crashlytics) | All | Critical | Not Started
75 | Legal | PDPA | Privacy policy covers PDPA requirements | All | Critical | Not Started
76 | Legal | Terms | Terms of Service accessible in-app | All | Critical | Not Started
77 | Legal | Disclaimer | Nutritional data disclaimer: "Estimates only. Not medical advice." | All | Critical | Not Started | Liability protection
78 | Go-to-Market | Launch | Landing page live with app store links + value prop | Web | High | Not Started
79 | Go-to-Market | Launch | Soft launch plan: 500 beta users from SG fitness communities | N/A | High | Not Started | r/singapore, HWZ, Telegram groups
80 | Go-to-Market | Feedback | In-app feedback mechanism (feedback button in Settings) | All | High | Not Started
81 | Go-to-Market | ASO | App Store keywords: "calorie tracker singapore", "macro food near me" | iOS/Android | High | Not Started