## Compressed Log
Date | Area | Change / Decision | Impact | Status
FOUNDATION — Early 2026
Early 2026 | Architecture | Next.js 14 + Firebase Auth + Zustand + Vercel | Full app scaffold live | ✅ Done
Early 2026 | Onboarding | 4-step wizard: Goal→Diet→Body→Account. Calculates BMR/TDEE/macros | Users get personalised calorie targets | ✅ Done
Early 2026 | Eat Tab | GPS nearby restaurants → sgFoodDb match → menus with Protein/$ and diet badges | Core product differentiator live | ✅ Done
Early 2026 | Food Log | Manual entry + search. Activity log (MET). Water tracking | Users can log all nutrition | ✅ Done
Early 2026 | Dashboard | Calorie ring, macro bars, water ring, streak badge, daily challenges | Home screen functional | ✅ Done
Early 2026 | Move Tab | Nearby gyms/parks via Google Places above activity log | Gym discovery live | ✅ Done
Early 2026 | API Layer | All API routes with Firebase Admin auth. Typed apiClient.ts wrapper | Secure, typed server communication | ✅ Done
Early 2026 | Streak | SGT timezone-aware streak + longestStreak tracking | Gamification live | ✅ Done
Early 2026 | Scan Feature | Camera → Claude Haiku → USDA → log food | Accuracy too low for SG food — deferred | ⏸ Deferred
FOOD DATABASE EXPANSION — Apr–May 2026
2026-04-18 | Food DB | Initial 9 outlets: McDonald's, KFC, BK, Subway, Old Chang Kee, Ya Kun, BreadTalk, Gong Cha, 7-Eleven | First verified SG macros | ✅ Done
2026-05-21 | Food DB | Hawker dishes in SG_MACRO_FOODS: teh tarik, wonton mee, others. Source: HPB | Hawker macro estimates available | ✅ Done
2026-05-22 | Food DB | 30+ more chains added. Total: 40+ outlets, 520+ items. Wendy's, A&W, Jollibee, Popeyes, Nandos, Starbucks, LiHo, KOI, Cheers, FairPrice Xpress, SaladStop, Bonchon, Mixue + more | Full SG chain coverage | ✅ Done
CODE FIXES — 2026-05-29
2026-05-29 | Bug Fix | Food search returned No results — rewired to sgFoodDb directly | Food search now works | ✅ Not pushed
2026-05-29 | Bug Fix | Protein/$ sort ranked Vanilla Soft Serve #1. Added 10g protein floor | Ranking shows real value meals | ✅ Not pushed
2026-05-29 | UX | Post-onboarding redirect /dashboard → /eat | New users see GPS food discovery first | ✅ Not pushed
2026-05-29 | Data Fix | McDonald's cone price corrected $0.50 → $1.00 | Protein/$ score accurate | ✅ Not pushed
2026-05-29 | Navigation | Eat tab moved to first position in bottom nav (Eat·Log·Home·Move·Me) | Food discovery is the core feature | ✅ Not pushed
2026-05-29 | UX | Open Now filter hidden — not backed by real business hours data | Stops showing incorrect availability | ✅ Not pushed
2026-05-29 | UX | Scan page replaced with Coming Soon card + redirect hint to Log/Eat | Clear user expectation | ✅ Not pushed
2026-05-29 | Wiring | Me page: syncProfileFromServer() added on mount | Profile always shows live data | ✅ Not pushed
2026-05-29 | Landing Page | Transformed landing page into open food discovery search. Live searchAll() results, no auth required. Sign up only prompted on Log action. | Discovery open to everyone — no sign-up wall | ✅ Not pushed
2026-05-29 | Tooling | Generated Stride_Price_Audit.xlsx (522 items from 40+ outlets for GrabFood price verification) | Price audit ready to run | ✅ Done
STRATEGIC DECISIONS — 2026-05-29
2026-05-29 | Principle | Reliability is #1 priority above new features. Wrong data destroys trust faster than missing features. | Every feature decision filtered through data reliability first | ✅ Decided
2026-05-29 | Data Process | All sgFoodDb updates need source, verified flag, lastVerified date. Quarterly price sweeps via GrabFood. | Traceable, auditable food database | ✅ Decided
2026-05-29 | Scan Feature | Scan deferred not cancelled. Revisit when SG food recognition improves or barcode scan built as simpler step. | No inaccurate AI food ID shipped | ⏸ Deferred — revisit
2026-05-29 | Exercise | Structured workout routines → Phase 2. Activity logging (MET) already live. | Nutrition MVP first | 🔵 Phase 2
2026-05-29 | GrabFood/Foodpanda | Two paths: scrape (legal risk) or official data partnership. Evaluate post-MVP. | Manual GrabFood for now; partnership long-term | ⏳ Open
2026-05-29 | Notifications | Push notifications (daily reminders, streak alerts) → Phase 2 via Firebase FCM. | Build after core reliability confirmed | 🔵 Phase 2
2026-05-29 | Rewards | Deeper gamification (badges, XP, leaderboards) → Phase 2. Streak + challenges already live. | Accurate data retains users more than rewards | 🔵 Phase 2
FOOD SEARCH — DIETARY FOCUS DECISIONS — 2026-05-29
2026-05-29 | Product Direction | Food search focused on dietary restriction users: Halal, High Protein, Vegetarian, Vegan, Allergies — in priority order | Most motivated users, highest return rate, underserved by existing SG apps | ✅ Decided
2026-05-29 | Schema | Add allergens?: string[] to SGMenuItem. Lists what item CONTAINS. Only populate from official_sg/hpb. Community items show no allergen data. | Physical safety — wrong allergen data could cause reactions. Never show unverified claims. | ✅ Decided
2026-05-29 | Data Rule | Halal: item-level tagging, audit certified vs mixed. Vegan: official sources only, conservative. Vegetarian: audit pass needed. High Protein: already in data. | Fewer accurate tags beat many inaccurate ones | ✅ Decided
PENDING — Not Yet Done
TBD | Deploy | Push all code changes to git. Run: git add -A && git commit && git push origin main from local terminal | All fixes go live on Vercel | ⏳ Pending
TBD | Navigation | Logged-in users: confirm whether /eat should also be the default landing after login (not just post-registration) | Eat tab as universal home | ⏳ Open
TBD | Database | Halal audit (certified vs mixed outlets). Allergens field added to schema and populated from official PDFs. Vegetarian/vegan tag audit. | In order: Halal → Allergens → Vegetarian → Vegan | ⏳ Pending
TBD | Price Audit | Fill Stride_Price_Audit.xlsx against GrabFood outlet by outlet. Send back for Claude to apply corrections. | All 520+ item prices verified | ⏳ Pending
TBD | Dashboard | Wire dashboard to loadTodayFromServer on mount. Improve empty state for first-time users. | Dashboard shows live data, better first-run experience | ⏳ Pending
DATABASE SCHEMA DECISIONS — 2026-05-29
2026-05-29 | Schema | Single meals table, nullable restaurant_id. Per-serving macros only (compute per-100g). Boolean diet tag columns. Three-state allergens (null/true/false). Price range for generic dishes. | Full schema defined in DATABASE_SCHEMA.md | ✅ Decided
2026-05-29 | Schema | Dedup: canonical_name UNIQUE + fuzzy match on submit + duplicate rows kept with self-FK (never delete — protects user logs) | Prevents MyFitnessPal naming problem | ✅ Decided
2026-05-29 | Schema | Community stats: separate pre-aggregated table, recomputed on feedback approval. Show only when count>=3. Range display when std_dev>20%. | Fast queries, reliable community data display | ✅ Decided
2026-05-29 | Docs | DATABASE_SCHEMA.md created in OneDrive Fitness App root. Full SQL schema, design decisions, sgFoodDb mapping, display rules. | Single source of truth for schema | ✅ Decided
TBD | Implementation | Implement allergens field in sgFoodDb.ts TypeScript schema + populate from official SG PDFs for top chains | Allergen data live for Stride Approved meals | ⏳ Pending
INFRASTRUCTURE DECISION — 2026-05-29
2026-05-29 | Platform | Stay on Firebase/Firestore. Four collections: /restaurants, /meals, /meal_feedback, /meal_community_stats. sgFoodDb.ts stays as client-side search layer. | No second backend. Search stays fast and offline. Community stats via Cloud Function. | ✅ Decided
ALLERGEN SCHEMA & MVP DECISION — 2026-05-29
2026-05-29 | Schema | SGAllergens interface + allergens?: SGAllergens field added to SGMenuItem. Three-state: true=contains, false=verified free, null=unknown. | Schema ready for data population | ✅ Done
2026-05-29 | Data | McDonald's 11 items populated with allergen data. Some fields still null (McSpicy eggs, Fries shared fryer, Cone mix) — need official PDF verification. | First real allergen data in the system | ✅ Done
2026-05-29 | Decision | Allergen data logged in schema but NOT displayed in app UI for MVP. Too dangerous to show partial/unverified allergen claims. Phase 2: verify nulls from official SG PDFs, then build UI display. | Safety over completeness — log now, display later | ✅ Decided
TBD | Data | KFC, Subway, Burger King, and all other outlets: allergen fields not yet populated. Dean to populate from official SG allergen PDFs/guides. | Full allergen coverage across all outlets | ⏳ Pending
TBD | UI | Build allergen display layer in Eat tab and Log tab. Show badges only for source='official_sg'¦'hpb'. Always include disclaimer. | Allergen filtering live for users | ⏳ Pending

## Decision Log
Date | Decision Area | Decision Made | Why / Reasoning | Alternatives Considered | Status
FOOD RANKING & SCORING
Early 2026 | Ranking Metric | Use Protein/$ (g per SGD) as primary food value score | Budget-conscious SG users. Protein is hardest macro to optimise cheaply. Protein/$ lets users find best value high-protein meals near them — core product differentiator. | Calorie/$ (too broad), Protein/calorie (ignores price), Raw protein (ignores value) | ✅ Live
Early 2026 | Protein/$ Formula | proteinPerDollar = round((protein/price)×10)/10 | Simple, transparent, one decimal. Users can verify mentally. 30g protein at $5 = 6.0 g/$ | Weighted composite score (too opaque), Protein density (ignores price) | ✅ Live
2026-05-29 | Protein/$ Minimum Floor | Items with <10g protein score 0 in Protein/$ ranking — fall to bottom | Without floor, cheap desserts dominated. Vanilla Soft Serve at $0.50/4g scored 8 g/$ and ranked #1 above KFC chicken (29g, 7.6 g/$). Metric meaningless below minimum protein threshold. | 5g floor (too low), 20g floor (too aggressive), No floor (broken ranking) | ✅ Live
RESTAURANT & SCHEMA DESIGN
Early 2026 | RestaurantTier Schema | 3 tiers: full_menu (verified chain), estimated_menu (hawker, uses macroDbRef), place_only (GPS only, no menu data) | Chains have official nutrition PDFs. Hawker stalls vary by cook — use HPB estimates. place_only avoids showing bad data. | Single tier with confidence flags (harder for frontend), No tiers (forced all to show data) | ✅ Live
Early 2026 | serviceTypes Array | serviceTypes always an array: ['dine_in','grab_go','delivery'] — never a single string | Outlets can serve multiple modes. Array future-proofs filter logic. | Single string field (breaks multi-mode outlets), Boolean flags per type (verbose) | ✅ Live
Early 2026 | macroDbRef Field | estimated_menu items reference SG_MACRO_FOODS via macroDbRef string ID instead of duplicating macro values | Single source of truth — update one entry, all hawker outlets reflect it. Avoids sync issues. | Duplicate macros per outlet (gets out of sync), Always hardcode (no shared source) | ✅ Live
Early 2026 | Local TypeScript vs Firestore | Store SG restaurant/menu data in sgFoodDb.ts (local TypeScript), not Firestore | Zero latency, works offline, no Firestore read costs, type-safe. Community user foods go to Firestore separately. | All Firestore (latency+cost), JSON file (no type safety), Both duplicated (sync problem) | ✅ Live
Early 2026 | Source Verification Flags | Every item: source ('official_sg'¦'hpb'¦'community'¦'usda') + verified: bool + lastVerified date | Macro accuracy varies by source. Every entry must be traceable. Enables prioritising corrections. | Single verified boolean (loses source info), No flags (no way to prioritise corrections) | ✅ Live
UX & NAVIGATION DECISIONS
2026-05-29 | Post-Onboarding Routing | After registration redirect to /eat instead of /dashboard | New users have no logged data — empty dashboard. Eat tab shows immediate value: GPS food discovery. First impression = core differentiator, not empty chart. | Stay on /dashboard (empty state), Onboarding tips screen (more work, deferred) | ✅ Live
2026-05-29 | Eat Tab First in Nav | Eat tab moved to position 1 in bottom nav (was position 3). Order: Eat·Log·Home·Move·Me | Food discovery is the core differentiator — should be first and most accessible. Dashboard is useful once user has data, but Eat is action-oriented from day 1. | Keep Dashboard first (generic, empty for new users) | ✅ Not pushed
2026-05-29 | Open Discovery Landing | Landing page transformed: live food search with no auth required. Sign up only prompted on Log action. | Largest, most frequent behaviour is deciding what to eat — not calorie tracking. Discovery without auth removes the biggest barrier to first-value. Choo Ming Hao's input: position as fastest way to decide what to eat, not another calorie tracker. | Auth wall before any search (high drop-off), Pure marketing page (no immediate value) | ✅ Not pushed
2026-05-29 | Scan Feature Deferral | Scan is deferred not cancelled. Show Coming Soon card. Revisit when SG food recognition improves or barcode scan built as simpler step. | Claude Haiku misidentifies SG dishes. Shipping inaccurate scan damages trust more than not having it. | Ship with low-confidence warning (still wrong), Restrict to packaged barcodes only (different feature) | ⏸ Deferred — revisit
DIETARY FOCUS & TAG DECISIONS — 2026-05-29
2026-05-29 | Target User — Dietary Restrictions | Primary focus for food search: users with dietary restrictions or targeted food preferences. Priority order: (1) Halal (2) High Protein (3) Vegetarian (4) Vegan (5) Allergies | These users have no alternative — generic apps don't filter accurately for SG food. Most motivated, highest return rate, real underserved pain point. Choo Ming Hao partnership — database is Dean's responsibility. | Target all users equally (no differentiation), Fitness/macro users only (smaller audience) | ✅ Decided
2026-05-29 | Allergen Schema Design | Add allergens?: string[] to SGMenuItem. Lists what item CONTAINS. SG allergens: gluten, dairy, eggs, peanuts, tree nuts, shellfish, soy, sesame. | Listing contained allergens is safer than claiming free-from. Official SG PDFs list contained allergens — maps directly to source data. If we say nut-free and are wrong, someone has a reaction. If we list contained and miss one, user is more likely to double-check. | freeFrom: string[] (makes promises we can't guarantee), Boolean per allergen (verbose, hard to query) | ✅ Decided
2026-05-29 | Allergen Reliability Rule | Show allergen data ONLY for source='official_sg' or 'hpb'. All other items show: 'Allergen info not available — check with restaurant.' Add disclaimer on all allergen displays. | Wrong allergen data has physical safety consequences. Wrong calories = inconvenience. Wrong allergens = anaphylaxis risk. Showing nothing is always safer than showing unverified claims. | Show community estimates with warning (still shows wrong data), Block all allergen display (loses feature value) | ✅ Decided
2026-05-29 | Halal Tag Precision | Distinguish: (A) Fully halal-certified outlet — entire menu halal. (B) Mixed outlet — halal counter within non-halal venue. (C) Not halal. Tag at item level for mixed outlets. | Some food courts have halal stalls in non-halal environments. Blanket outlet-level halal tagging inaccurate for mixed venues. Muslim users need to know the difference. compatibleWith[] at item level already supports this. | Outlet-level only (inaccurate for mixed venues), No halal tracking (loses key SG demographic) | ✅ Decided
2026-05-29 | Vegan Conservative Approach | Only tag vegan when explicitly confirmed by official_sg/hpb. SG cooking uses hidden animal products: oyster sauce, fish sauce, lard, egg in noodles, shrimp paste in sambal. When in doubt, do not tag as vegan. | Vegan users have highest sensitivity to wrong tags — one mistake breaks trust permanently. SG cuisine has many hidden animal derivatives. Fewer verified vegan options better than many unverified ones. | Tag based on ingredient assumption (high false positive risk), Skip vegan entirely (loses vegan segment) | ✅ Decided
ONGOING PRINCIPLES
2026-05-29 | Core Priority | Reliability #1 above all features. Wrong data destroys trust faster than missing features. | Users making food/fitness decisions based on bad data lose trust and never return. Every feature decision must ask: does this make data more or less reliable? | Features-first (deferred reliability), Best-effort data (acceptable for v1) | ✅ Decided
2026-05-29 | Data Push Reliability | Optimistic UI + background sync. Never block UI on Firestore write. Always verify correct field names, types, subcollection paths. | Users should never wait for server response. Silent failures lose data. Schema discipline prevents silent corruption. | Await all writes (UI feels slow), Fire-and-forget no validation (data corruption risk) | ✅ Decided
2026-05-29 | Price Verification Process | Quarterly price sweeps using GrabFood as primary. Corrections applied via audit spreadsheet → Claude → sgFoodDb in one pass. | Prices change more than macros. McDonald's cone was $0.50 in DB, $1.00 in real life. GrabFood always shows live SG prices. Batch correction faster than line-by-line editing. | Manual ad-hoc fixes (too slow, misses items), Automated scraping (legal risk, maintenance) | ✅ Decided
FUTURE ROADMAP
2026-05-29 | Exercise Routines | Structured workout routines → Phase 2. /workouts stub exists. Build after nutrition MVP stable. | Splitting focus before nutrition is solid risks doing both poorly. | Build now alongside food (splits focus) | 🔵 Future — Phase 2
2026-05-29 | GrabFood/Foodpanda | Two paths: (A) scrape menu+price data for auto-sync, (B) official data partnership. Evaluate post-MVP. | Scraping is legally grey and fragile. Partnership is right long-term but needs leverage/traction first. | Build scraper now (legal risk), Partnership now (too early) | ⏳ Open
2026-05-29 | Push Notifications | Daily reminders, streak alerts, weekly recap → Phase 2 via Firebase FCM. | Notifications before reliability is confirmed drive uninstalls. Build when data is trusted. | Build now (distraction from reliability) | 🔵 Future — Phase 2
2026-05-29 | Rewards & Gamification | Deeper gamification (badges, XP, leaderboards) → Phase 2. Streak + daily challenges already live. | Accuracy retains users more than rewards at this stage. | Full XP system now (over-engineered for MVP) | 🔵 Future — Phase 2
2026-05-29 | Scan Feature Revisit | Revisit scan when: (1) SG-specific food recognition dataset exists, or (2) barcode scan for packaged goods built as simpler first step. | SG dishes have no reliable training data in general vision models. Barcode for NTUC/Cheers products is more solvable short-term. | Ship with low-confidence warning, Use USDA only (no SG dishes) | ⏸ Deferred — revisit
DATABASE SCHEMA DECISIONS — 2026-05-29
2026-05-29 | Schema: Meal Table Structure | Single meals table with nullable restaurant_id for all food items (restaurant menu items AND generic hawker/HPB dishes) | Both types share 90% of fields. Two separate tables would duplicate search logic and require UNION queries. restaurant_id=NULL cleanly distinguishes generic dishes from outlet-specific items. | Two separate tables: restaurant_meals + generic_meals (JOIN complexity, duplicate search logic) | ✅ Decided
2026-05-29 | Schema: Macros Storage | Store macros per serving + serving_size_g only. Never store per-100g — always compute: macro_per_100g = (macro / serving_size_g) × 100 | Storing both creates a sync problem: if serving_size_g is corrected, pre-computed per-100g values become stale. Single source of truth is the per-serving values. | Store both per-serving and per-100g (sync risk), Store only per-100g (loses serving context) | ✅ Decided
2026-05-29 | Schema: Diet Tag Columns | Core diet tags as boolean columns (is_halal, is_vegetarian, is_vegan, is_keto, is_gluten_free, is_high_protein). Extras in diet_tags_extra TEXT[]. | Boolean columns are indexed and fast: WHERE is_halal=true AND is_vegan=true uses B-tree index. Array @> operator requires GIN index and is slower. is_high_protein is computed (protein_g >= 25) but stored as column so it is indexed. | Single TEXT[] column for all tags (slow array queries), JSON column (no indexing), Bitmask integer (unreadable) | ✅ Decided
2026-05-29 | Schema: Allergen Three-State | Allergen columns are BOOLEAN? (nullable): NULL=unknown (show nothing), TRUE=contains (show warning), FALSE=verified free (show with disclaimer). Only populated from official_sg or hpb sources. | Wrong allergen data causes physical harm. NULL forces the app to show nothing rather than a wrong claim. False-negative allergen labelling (saying nut-free when it is not) could cause anaphylaxis. Showing nothing is always safer than showing unverified absence claims. | Boolean only true/false (no unknown state), Text array of allergens present (no verified-free state), Skip allergens entirely | ✅ Decided
2026-05-29 | Schema: Price Fields | Restaurant items: single price_sgd. Generic dishes: price_min_sgd, price_max_sgd, price_typical_sgd range. Both types have all four columns; unused ones are NULL. | Chicken rice is $3.50 at a hawker and $12 at a hotel. A single price field is misleading for generic dishes. A range with a typical value gives users useful context. Restaurant items always have a fixed price from the official menu. | Single price field for all (misleading for generic dishes), Always store ranges (unnecessary for fixed-price restaurant items) | ✅ Decided
2026-05-29 | Schema: Deduplication | canonical_name (UNIQUE) + aliases[] + status (active/duplicate/archived) + canonical_meal_id self-FK. Fuzzy match on submission: >80% = block, 60-80% = warn. Duplicate rows are never deleted — they stay with status=duplicate pointing to canonical. | MyFitnessPal failure: unchecked community entries created thousands of near-duplicate meals. Prevention (fuzzy match on submit) + cleanup (admin merge queue) is the solution. Keeping duplicate rows protects existing user food logs that reference them. | Delete duplicates (breaks user food logs), No deduplication (MyFitnessPal problem), Manual only with no system enforcement | ✅ Decided
2026-05-29 | Schema: Community Stats Separation | meal_community_stats is a separate table, recomputed when feedback is approved. Never aggregate at query time. Show community data only when feedback_count >= 3. Show range (not average) when std_dev_calories > 20% of avg. | Recomputing averages across thousands of feedback rows on every search query is too slow. Pre-aggregated stats give instant reads. std_dev is a reliability signal: high variance means the community does not agree on the macros — show a range instead of a misleading precise number. | Compute averages on every query (too slow at scale), Show all feedback regardless of count (n=1 is unreliable) | ✅ Decided
2026-05-29 | Schema: Confidence Tier Display | Three tiers: stride_approved (official_sg/hpb + verified) shows allergens + full data. community (feedback_count>=3) shows macros + Community badge, no allergens. stride_estimate (usda/extracted) shows macros + Estimate badge, no allergens. | Users need to know how much to trust the data they see. Allergen data is only shown when we have official verification — community and estimated items never show allergen claims regardless of confidence. | No confidence display (users cannot assess data quality), Single verified/unverified flag (loses source context) | ✅ Decided
INFRASTRUCTURE DECISION — 2026-05-29
2026-05-29 | Database Platform | Stay on Firebase / Firestore. Food database built as Firestore collections. Do NOT migrate to Supabase. | Already set up, already paid for, already wired to auth and user data. Choo Ming Hao's roadmap listed Supabase as an option, but splitting to two backend services adds unnecessary complexity at this stage. Firestore collections map directly to the schema we designed. | Supabase/PostgreSQL (clean SQL but adds second backend service, migration cost, extra complexity) | ✅ Decided
2026-05-29 | Firestore Collection Structure | Four collections: /restaurants/{id}, /meals/{id}, /meal_feedback/{id}, /meal_community_stats/{mealId}. meal_community_stats uses same ID as the meal document it aggregates. | Direct mapping of the schema tables to Firestore collections. meal_community_stats keyed by meal ID enables single-document lookup without a query. | Subcollections under meals (harder to query across meals), Single flat collection (no separation of concerns) | ✅ Decided
2026-05-29 | Firestore: Search Strategy | Keep sgFoodDb.ts as the client-side search layer (fast, offline, no Firestore reads). Use Firestore for persistence, user feedback, and community stats only. Algolia can be added later if search scale demands it. | Firestore cannot do substring text search (no LIKE queries). sgFoodDb.ts already provides fast client-side search via searchAll(). This avoids paying for Algolia at MVP stage while keeping search fast. Firestore array-contains works for exact alias matching. | Algolia now (cost, complexity at MVP stage), Firestore-only search (no substring support without workarounds) | ✅ Decided
2026-05-29 | Firestore: Computed Fields | is_high_protein and confidence_tier are computed at write time and stored as explicit fields. Do not derive on read. | Firestore has no computed columns. Storing pre-computed values keeps reads fast and queries simple. is_high_protein = protein_g >= 25, set on every meal write/update. | Compute on read (slower, more code), Cloud Functions for computation (over-engineered for two fields) | ✅ Decided
2026-05-29 | Firestore: Community Stats Update | meal_community_stats document updated via Cloud Function triggered on meal_feedback status change to 'approved'. Never aggregate at query time. | Firestore has no native aggregation. Pre-aggregated document is read in a single document fetch at query time. Cloud Function keeps it current without blocking the user-facing write. | Aggregate on every read (too slow at scale), Client-side aggregation (race conditions, inconsistent) | ✅ Decided
ALLERGEN MVP STRATEGY — 2026-05-29
2026-05-29 | Allergen Display — MVP Decision | Allergen data is logged in sgFoodDb.ts schema but NOT displayed in the app UI for MVP. Post-MVP, display only after full verification from official SG PDFs. | Incomplete allergen data shown in the UI is more dangerous than showing none. A user with a peanut allergy who sees 'peanuts: false' on an unverified item may be seriously harmed. The right order: log everything now → verify against official SG allergen PDFs → build UI display only after verification is complete. | Show available allergen data now with a disclaimer (still shows unverified claims), Skip allergen logging entirely (loses data we've already gathered) | ✅ Decided
2026-05-29 | Allergen Data — Phase Plan | Phase 1 (now): log allergen data as researched, null for unknowns, no UI display. Phase 2 (post-MVP): verify all null fields from official SG PDFs, build UI display for official_sg/hpb items only, add disclaimer on all allergen info shown. | Separating logging from display lets us capture data progressively without creating a safety risk. McDonald's SG top items partially populated. KFC, Subway, and all other outlets still need population. UI layer not yet built. | Build display and data together (blocks on full verification), Log and display simultaneously (safety risk with partial data) | ✅ Decided
2026-05-29 | Allergen Schema Implementation | SGAllergens interface added to sgFoodDb.ts. allergens?: SGAllergens field added to SGMenuItem. McDonald's 11 core items populated with allergen data (mix of true/false/null). MVP notice comment added at top of interface. | Schema is in place and typed correctly. null fields on McDonald's items (McSpicy coating eggs, fries shared fryer, Cone soft serve mix) need verification from mcdonalds.com.sg allergen PDF before being set to true/false. | No schema yet (delays future implementation), Full population before schema (puts content before structure) | ✅ Done

## Detailed Log
Date | Session | Type | What Was Done | File(s) Changed | Status | By | Notes
FOUNDATION BUILD — Early 2026
Early 2026 | 1 | Feature | Firebase Auth (email/password), Zustand store, Tailwind CSS, Vercel deployment | src/lib/firebase.ts, store.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | 4-step onboarding wizard. Calculates BMR/TDEE/macros using Mifflin-St Jeor | src/app/register/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Dashboard: calorie ring, macro bars, water ring, streak, challenges | src/app/(dashboard)/dashboard/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Eat tab: GPS → sgFoodDb match → menus with Protein/$ and diet badges | src/app/(dashboard)/eat/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Food log, activity log, water tracking | src/app/(dashboard)/log/ | ✅ Done | Dev
Early 2026 | 1 | Feature | Move tab: nearby gyms + parks via Google Places | src/app/(dashboard)/move/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | Me tab: profile, streak, weight log, sign out, reset | src/app/(dashboard)/me/page.tsx | ✅ Done | Dev
Early 2026 | 1 | Feature | All API routes with Firebase Admin auth. verifyToken() on every route. | src/app/api/*/route.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Streak system: SGT timezone-aware, longestStreak tracking | src/app/api/streak/route.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Recommendations engine: 8 rules, SGT-aware | src/app/api/recommendations/route.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Google Places cache: 10-min TTL, 1km grid | src/app/api/nearby-places/route.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Typed API client wrapper | src/lib/apiClient.ts | ✅ Done | Dev
Early 2026 | 1 | Feature | Scan: camera → Claude Haiku → USDA → log | src/app/(dashboard)/scan/page.tsx | ⏸ Deferred | Dev | SG food accuracy too low
FOOD DATABASE EXPANSION — Apr–May 2026
2026-04-18 | 2 | Data | Initial 9 outlets with official SG macros | src/lib/sgFoodDb.ts | ✅ Done | Dev
2026-05-21 | 3 | Data | Hawker dishes in SG_MACRO_FOODS (teh tarik, wonton mee, etc). Source: HPB | src/lib/sgFoodDb.ts | ✅ Done | Dev
2026-05-22 | 4 | Data | 30+ chains added. Total: 40+ outlets, 520+ items | src/lib/sgFoodDb.ts | ✅ Done | Dev | Wendy's, A&W, Jollibee, Popeyes, Starbucks, Mixue, LiHo, KOI, Cheers, FairPrice Xpress + more
CODE FIXES & IMPROVEMENTS — 2026-05-29
2026-05-29 | 5 | Bug Fix | Food search returned No results — rewired to search sgFoodDb directly (searchAll + SG_MACRO_FOODS + Firestore fallback) | src/app/(dashboard)/log/food/page.tsx | ✅ Not pushed | Claude | Was querying empty Firestore. Results capped at 30, deduped by ID.
2026-05-29 | 5 | Bug Fix | Protein/$ sort ranked Vanilla Soft Serve #1. Added MIN_PPD_PROTEIN=10g floor in both sort locations. | src/app/(dashboard)/eat/page.tsx | ✅ Not pushed | Claude | Fixed in individual item sort and restaurant-level sort.
2026-05-29 | 5 | UX | Post-onboarding redirect /dashboard → /eat | src/app/register/page.tsx | ✅ Not pushed | Claude
2026-05-29 | 5 | Data | McDonald's cone price $0.50 → $1.00. lastVerified updated. | src/lib/sgFoodDb.ts | ✅ Not pushed | Claude
2026-05-29 | 5 | Navigation | Eat tab moved to position 1 in bottom nav. Order: Eat·Log·Home·Move·Me | src/components/layout/BottomNav.tsx | ✅ Not pushed | Claude
2026-05-29 | 5 | UX | Open Now filter hidden — no real business hours data behind it | src/app/(dashboard)/eat/page.tsx | ✅ Not pushed | Claude
2026-05-29 | 5 | UX | Scan page: replaced upload button with Coming Soon card + redirect hint to Log/Eat tabs | src/app/(dashboard)/scan/page.tsx | ✅ Not pushed | Claude
2026-05-29 | 5 | Wiring | Me page: added syncProfileFromServer() on mount with offline catch | src/app/(dashboard)/me/page.tsx | ✅ Not pushed | Claude
2026-05-29 | 5 | Product | Landing page transformed into open food discovery search. searchAll() + SG_MACRO_FOODS live search, diet filters, sort options, Protein/$ cards. Sign up prompted only on Log action. | src/app/page.tsx | ✅ Not pushed | Claude | No auth required to search. Supports Halal/Vegan/Vegetarian/High Protein filters. GPS strip gates to sign up.
PENDING
TBD | — | Deploy | git add -A && git commit && git push origin main from local terminal | All files above | ⏳ Pending | Dean | Cannot push from Claude sandbox on OneDrive folder
TBD | — | Schema | Add allergens?: string[] field to SGMenuItem interface in sgFoodDb.ts | src/lib/sgFoodDb.ts | ⏳ Pending | Dean+Claude | Only populate from official_sg/hpb sources
TBD | — | Data | Halal audit: certified vs mixed outlet tagging across all 40+ outlets | src/lib/sgFoodDb.ts | ⏳ Pending | Dean
TBD | — | Data | Allergen data population from official SG PDFs (McDonald's, KFC, Subway, etc.) | src/lib/sgFoodDb.ts | ⏳ Pending | Dean
TBD | — | Data | Vegetarian tag audit — add missing tags to clearly vegetarian items | src/lib/sgFoodDb.ts | ⏳ Pending | Dean
TBD | — | Data | Vegan tag audit — conservative, official sources only | src/lib/sgFoodDb.ts | ⏳ Pending | Dean
TBD | — | Data | Complete price audit using Stride_Price_Audit.xlsx + GrabFood | src/lib/sgFoodDb.ts | ⏳ Pending | Dean+Claude
TBD | — | UX | Dashboard empty state for first-time users | dashboard/page.tsx | ⏳ Pending | Claude
TBD | — | UX | Add skeleton loaders across all pages | All dashboard pages | ⏳ Pending | Claude

## Summary
STRIDE — PROJECT SUMMARY & HANDOFF
Updated: 2026-05-29 ¦ Live: https://stride-app-rosy.vercel.app
WHAT IT IS
Stride is a fitness and nutrition tracking app for Singapore users. Core differentiator: GPS-based nearby restaurant discovery with verified Singapore macros and Protein/$ value score.
Stack: Next.js 14 · Firebase Auth + Firestore · Zustand · TypeScript · Tailwind CSS · Vercel
Working directory: C:\Users\user\OneDrive\Fitness App (shared collaborative OneDrive — ALL work here)
DIVISION OF RESPONSIBILITY
Dean: Database — sgFoodDb.ts. Research, verification, tagging (Halal, Protein, Vegan, Vegetarian, Allergens).
Choo Ming Hao: UI/Interface — food search front-end design and flow.
Claude: Code implementation, bug fixes, schema, documentation.
CURRENT BUILD STATUS (2026-05-29)
✅ App is MVP-ready. All core features work on mobile.
✅ Open discovery landing page — anyone can search without signing up.
✅ 40+ SG outlets, 520+ menu items, SG_MACRO_FOODS hawker dishes.
⚠️ All code fixes written but NOT YET pushed — run git push from local terminal.
⏸ Scan feature deferred (SG food ID accuracy too low).
NEXT IMMEDIATE STEPS (in order)
1. PUSH: git add -A && git commit && git push origin main (from local terminal)
2. Add allergens?: string[] to SGMenuItem schema
3. Halal audit — certified vs mixed outlet tagging
4. Populate allergen data from official SG PDFs (McDonald's, KFC, Subway publish these)
5. Vegetarian tag audit — add missing tags
6. Complete price audit (Stride_Price_Audit.xlsx + GrabFood sweep)
KEY DIETARY TAG DECISIONS
Priority: Halal (easiest, largest SG market) → High Protein (already in data) → Vegetarian → Vegan (conservative) → Allergies
Allergens: list what item CONTAINS — never claim free-from. Official sources only. Add disclaimer always.
Vegan: official sources only. SG food has hidden animal products (oyster sauce, fish sauce, lard, shrimp paste).
Halal: item-level tagging. Distinguish certified vs mixed-venue stalls.
KEY FILES
CLAUDE.md — Full developer guide. Read first in any new session.
CHANGELOG.md — Running fix log, most recent first.
PARTNER_BRIEFING.md — Paste into any new chat for full context.
Stride_Work_Log.xlsx — This file. Update after every session.
Stride_Price_Audit.xlsx — 522-item price verification spreadsheet.
src/lib/sgFoodDb.ts — SG food database (~13,000 lines, 40+ outlets).