## Overview
Stride — Roadmap & Launch Plan
Singapore-first one-stop health app. Track. Monitor. Eat Smart. Move Nearby. ¦ Prepared April 2026
Field | Value
Owner | Ming
Stage today | MVP build — Phase 1 (Q2 2026)
Launch market | Singapore (sole market through 2026)
Product spec | v2.0 simplified (April 2026): 4 pillars, 5-tab nav
Pillars | 1) Track 2) Monitor 3) Eat Smart 4) Move Nearby
Data moat | 352 verified SG SKUs (7-Eleven + NTUC FairPrice); growing to 3,500
Monetisation | Freemium: Stride+ S$6.90/mo ¦ Provider listings ¦ Affiliate ¦ Corporate
North-star metric | Weekly active users logging ≥3 days/week
Public launch target | Q3 2026 (App Store + Play Store, SG)
Year-1 MAU goal | 15,000 by end Q1 2027
Phase | Theme | Quarter | Go/no-go gate
Phase 1 | Product Launch | Q2 2026 | ≥70% of beta testers reach D3 retention
Phase 2 | App Enhancement & Testing | Q3 2026 | D30 retention ≥20%
Phase 3 | Marketing | Q4 2026 | 5,000 MAU & ≥3% Stride+ conversion
Phase 4 | User & Partner Onboarding | Q1 2027 | ≥1 anchor partner per category live
Tabs in this workbook
Tab | Purpose
Roadmap | Detailed workstream plan across the 4 phases (objective, owner, KPI, status)
Launch Checklist | Granular pre-launch checklist with status & owner
Marketing Plan | Channel, hypothesis, budget, success metric, lead/owner
Partner Pipeline | Anchor + self-serve partners; stage, value prop, status
Budget | Monthly cost & revenue ramp by phase with totals
KPI Dashboard | Targets across the 4 phases with formulas

## Roadmap
Stride Roadmap — 4 Phases x Workstreams
Each row is a workstream-level deliverable. Status drives the dashboard.
Phase | Workstream | Objective | Key activities | Owner | KPI / success | Status
Phase 1 Q2 2026 | Product | Lock v2.0 spec & ship MVP | Build Home/Scan/Eat/Move/Me. Strip community, water, streak. Wire Apple Health + Fitbit sync. Onboarding 3-screen flow. | Ming + dev | MVP feature-complete by week 8 | In progress
Phase 1 Q2 2026 | Data | Seed SG nutrition DB | Load 352-SKU CSV; structure schema for community-add + confidence score; nightly verification job. | Ming | 352 SKUs live in app | In progress
Phase 1 Q2 2026 | QA & Testing | Internal dogfood + closed beta | 10–15 internal users for 2-week dogfood; bug bash; Crashlytics ≥99% crash-free; cold start <1.5s. | Ming | Closed TestFlight + Play beta open with 150 users | Planned
Phase 1 Q2 2026 | Compliance | PDPA-aligned data handling | Privacy policy, T&Cs, data export & delete flow, health permissions explainer screens. | Ming + legal | PDPA review complete | Planned
Phase 1 Q2 2026 | Launch ops | App Store + Play submission | App Store Connect setup, screenshots (5 SG-themed), keyword set, age rating, App Privacy form. | Ming | App Store + Play approval received | Planned
Phase 2 Q3 2026 | AI scan tuning | Improve photo accuracy on SG dishes | Curate 500 SG dish images; eval set; targeted retraining/few-shot; tap-to-correct flow that improves model. | Ming | Top-3 accuracy ≥80% | Planned
Phase 2 Q3 2026 | Wearables | Add Garmin + Google Fit | Garmin Connect IQ + Google Fit REST API; resolve duplicate-step issues for dual-device users. | Ming + dev | Garmin & Google Fit live in app | Planned
Phase 2 Q3 2026 | Database | Expand SG DB to 1,000 SKUs | Add Cold Storage, Cheers, FairPrice Xtra; community-add with confidence score; partner CSV pipeline. | Ming | ≥1,000 SKUs verified | Planned
Phase 2 Q3 2026 | Reliability | Production hardening | Crash-free ≥99.5%; latency budgets; battery audit; error monitoring & alerting. | Ming + dev | Crash-free sessions ≥99.5% | Planned
Phase 2 Q3 2026 | Body monitor | Smart-scale + BF% trend | Withings + Fitbit Aria integration; body fat % chart; weekly PDF export. | Ming | Smart-scale sync live; PDF export shipped | Planned
Phase 3 Q4 2026 | Creators | Coordinated creator wave | Sign 8–12 SG IG/TikTok creators; custom referral codes; 3-week burst calendar. | Ming | ≥8 creators live; CAC ≤ S$5 | Planned
Phase 3 Q4 2026 | App Store | Editorial featuring | Pitch Apple SEA + Google Play for Health/Fitness collection placement. | Ming | Featured in ≥1 collection | Planned
Phase 3 Q4 2026 | PR | SG tech & lifestyle press | Tech in Asia, e27, CNA Lifestyle, Daily SG; founder narrative; data moat angle. | Ming | ≥3 SG outlets covered | Planned
Phase 3 Q4 2026 | Monetisation | Stride+ subscription live | Hard paywall on advanced Eat filters, Move map, multi-wearable sync, weekly PDF; pricing test. | Ming | ≥3% conversion of MAU | Planned
Phase 3 Q4 2026 | Paid pilot | Meta/TikTok performance pilot | S$5k pilot with creator-style native creative; 3 audiences; CAC + retention readout weekly. | Ming | CAC ≤ S$8 with D7 ≥ 25% | Planned
Phase 4 Q1 2027 | Provider portal | Build self-serve dashboard | Menu CMS, calorie data, classes, promotions; verified badge logic; analytics view. | Ming + dev | Portal beta live | Planned
Phase 4 Q1 2027 | Anchor partners | Sign 1 per category | 1 wellness clinic, 1 gym chain, 1 healthier-eating chain, 1 supermarket, 1 corporate pilot. | Ming | ≥3–5 anchor partners live | Planned
Phase 4 Q1 2027 | Affiliate | Delivery deep-links | GrabFood + Foodpanda deep-links from Eat cards; affiliate tracking & rev share. | Ming | ≥1 delivery partner live; revenue tracked | Planned
Phase 4 Q1 2027 | Stride for Teams | Corporate wellness pilot | 1 corporate pilot (50–200 seats); HR dashboard; anonymised insights. | Ming + sales | 1 corporate pilot signed | Planned
Phase 4 Q1 2027 | Community v0 | Foundations only | Social Favorites (per ideas.md): see how many saved, community-curated lists. No full feed yet. | Ming | Favorites surface live | Planned

## Launch Checklist
Pre-Launch Checklist (Singapore)
Granular pre-launch tasks. Mark Status = Done as completed.
Area | Item | Detail | Owner | Due | Status
Product | Lock v2.0 spec | Sign-off on 4 pillars, 5-tab nav, screen-by-screen spec | Ming | Wk 1 | In progress
Product | Design system | Typography, spacing, hero number treatment, color tokens | Ming | Wk 2 | Planned
Product | Onboarding flow | 3-screen onboarding: goal, body baseline, permissions | Ming | Wk 7 | Planned
Product | Empty states & errors | Friendly empty states for Eat/Move when no nearby results | Ming | Wk 8 | Planned
Data | Seed SG DB (352 SKUs) | Import CSV v3; verify mapping; nightly checks | Ming | Wk 4 | In progress
Data | Confidence score schema | Set up community-add structure for Phase 2 | Ming | Wk 5 | Planned
AI | Photo scan baseline | Vision AI plumbed; eval set of 100 SG dishes | Ming | Wk 6 | Planned
AI | Tap-to-correct | User correction flow that captures training signal | Ming | Wk 8 | Planned
Wearable | Apple HealthKit | Steps, active kcal, weight read; permissions copy | Ming | Wk 5 | Planned
Wearable | Fitbit Web API | OAuth + daily sync; duplicate-step handling | Ming | Wk 6 | Planned
Eat | Google Places list view | Restaurant cards: name, cuisine, distance, kcal range | Ming | Wk 7 | Planned
Eat | Ready-to-eat cards | From SG DB; one-tap log; filter chips | Ming | Wk 7 | Planned
Move | Places map (gyms/parks) | Map pins by category; activity logger with kcal estimate | Ming | Wk 8 | Planned
Compliance | PDPA review | Privacy policy, data export & delete, age gating | Ming + legal | Wk 8 | Planned
Compliance | App Store privacy label | Apple App Privacy form; Google Data safety form | Ming | Wk 10 | Planned
QA | Internal dogfood | 10–15 trusted users for 2 weeks | Ming | Wk 9 | Planned
QA | Crashlytics & analytics | Sentry/Crashlytics + product analytics in place | Ming | Wk 9 | Planned
QA | Closed TestFlight + Play beta | 150 invited users; weekly cohort retention readout | Ming | Wk 10 | Planned
Launch | App Store screenshots & copy | 5 SG-themed screenshots; keyword set; subtitle | Ming | Wk 10 | Planned
Launch | Submission | App Store Connect + Play Console submission, age rating | Ming | Wk 11 | Planned
Launch | Soft launch | Public release; monitor crashes & ratings hourly first 72h | Ming | Wk 12 | Planned
Marketing | Landing page + waitlist | Single-page site, signup form, demo videos | Ming | Wk 6 | Planned
Marketing | Creator long-list | Long-list of 30 SG creators; outreach template | Ming | Wk 8 | Planned
BD | Anchor partner outreach | Warm intros to gym, restaurant, supermarket, clinic, corporate | Ming | Wk 6 | Planned
BD | First LOI | 1 anchor partner letter of intent signed | Ming | Wk 12 | Planned
Totals | Done
In progress
Planned
Total items
% Done

## Marketing Plan
Marketing Plan — Channels, Hypothesis, Budget
Test budgets per channel. Scale only when success metric is hit.
Channel | Hypothesis | Test budget (S$) | Success metric | Owner | Status
Creator partnerships (IG/TikTok) | Low CAC + social proof from local SG creators | 8000 | CAC ≤ S$5; >3% click-to-install | Ming | Planned
App Store SEO | Own 'calorie tracker Singapore' & related intent | 1000 | Top-3 SG ranking on 5 keywords | Ming | Planned
Reddit r/singapore + Telegram | High-trust SG niche communities; founder voice | 0 | Organic mentions; 2 AMAs | Ming | Planned
Partner co-marketing | Co-promote with anchor partners to bring their customers | 0 | ≥3 anchor partners co-promoted | Ming | Planned
Meta + TikTok paid | Performance pilot — only after PMF signal in retention | 5000 | CAC ≤ S$8; D7 ≥ 25% | Ming | Planned
PR (TIA, e27, CNA Lifestyle) | Founder + data moat narrative wins editorial attention | 0 | ≥3 SG outlets covered | Ming | Planned
Corporate wellness BD | B2B2C distribution via 1–2 anchor employers | 0 | 1 corporate pilot signed | Ming | Planned
HPB / Healthier SG outreach | Govt programmes amplify SG-native health apps | 0 | 1 introduction meeting | Ming | Planned
Referral program | Existing users invite friends for Stride+ trial extension | 1500 | Referral CAC ≤ S$3 | Ming | Planned
Newsletter / content SEO | Long-tail SG nutrition queries (e.g. 'NTUC ready meal calories') | 1000 | 1k organic visits/mo by Ph 4 | Ming | Planned
Total test budget

## Partner Pipeline
Partner Pipeline — Anchor + Self-serve
Sign 1 anchor per category before opening self-serve. Founding Partner badge for first 3 in each category.
Category | Target partner (example) | Value to Stride users | Stage | Est. value | Status
Healthier-eating chain | SaladStop! / Grain / The Daily Cut | Verified menu macros; Eat Smart surfacing | Outreach | Marketing co-promo + listing rev | Planned
Supermarket | NTUC FairPrice (expand) | Ready-meal cards with verified macros | Pre-discussion | Listing fees + data partnership | Planned
Convenience | 7-Eleven SG | Onigiri/wrap macros; in-app discovery | Pre-discussion | Listing fees + cross-promo | Planned
Gym chain | Anytime Fitness / True Fitness | Discovery via Move screen; class listings | Outreach | Listing + lead-gen rev share | Planned
Boutique studio | Ground Zero / Ritual Gym | Schedule integration; community discovery | Lead | Listing rev | Planned
Wellness clinic | Singapore-based nutrition clinic | Booking, plan delivery (Phase 3+) | Lead | Marketplace take-rate | Planned
Delivery app | GrabFood / Foodpanda | Pre-filtered orders by goal; deep-links | Lead | Affiliate commission | Planned
Corporate wellness | 1 mid-market employer (200–500 staff) | Stride+ for employees; HR dashboard | Outreach | S$8–12/seat/mo | Planned
Government / public | HPB Healthier SG partner programme | Distribution + credibility halo | Lead | Strategic / co-marketing | Planned
Wearable | Withings / Fitbit Aria | Smart-scale data into Monitor pillar | Pre-discussion | Strategic integration | Planned

## Budget
Monthly Budget — Cost & Revenue Ramp by Phase (S$)
Illustrative; re-baseline after Phase 1 closed beta retention readout.
Bucket | Phase 1 Q2 2026 | Phase 2 Q3 2026 | Phase 3 Q4 2026 | Phase 4 Q1 2027 | Total
COSTS
Cloud + AI inference | 500 | 1200 | 2500 | 4500
Tooling (analytics, monitoring, support) | 400 | 700 | 900 | 1200
Marketing (creators + paid) | 0 | 1000 | 8000 | 10000
Contractor (design / QA) | 2000 | 2000 | 2500 | 3500
Misc (legal, IP, compliance) | 500 | 500 | 800 | 1000
Total monthly costs
REVENUE
Stride+ subscription | 0 | 0 | 900 | 4500
Affiliate (delivery) | 0 | 0 | 200 | 1200
Provider listings | 0 | 0 | 0 | 2500
Corporate pilot | 0 | 0 | 0 | 2000
Total monthly revenue
Net monthly (Revenue − Cost)
Notes & assumptions
• Stride+ Phase 3: ~150 paying subs at S$6.20 net/mo; Phase 4: ~750 paying subs.
• Affiliate revenue assumes ~3% of Eat-screen sessions deep-link to delivery; ~3% of those convert.
• Provider listings assume 5 paying SMB partners @ S$199/mo + 1 Enterprise @ S$499/mo by Phase 4.
• Corporate pilot Phase 4: 1 employer @ ~200 seats × S$10/mo discounted = ~S$2,000/mo.
• Costs exclude founder time; assumes contractor hours on design/QA only.
• Re-baseline after Phase 1 closed beta retention curves are available.

## KPI Dashboard
KPI Dashboard — Targets by Phase
Targets only. Compare to actuals during weekly business review.
KPI | Phase 1 Q2'26 | Phase 2 Q3'26 | Phase 3 Q4'26 | Phase 4 Q1'27 | Trend (Ph1→Ph4)
MAU | 150 | 1500 | 5000 | 15000
D7 retention | 40% | 35% | 30% | 30%
D30 retention | — | 20% | 20% | 22% | n/a
AI scan top-3 accuracy | 70% | 80% | 85% | 87%
SG food DB SKUs | 352 | 1000 | 2000 | 3500
Stride+ conversion | — | — | 3% | 5% | n/a
Anchor partners live | 0 | 0 | 1 | 4 | n/a
App Store rating | 4.5 | 4.6 | 4.6 | 4.7
Stride+ paying subscribers | 0 | 0 | 150 | 750 | n/a
North-star metric
Weekly active users logging ≥3 days/week